## Sheet1
Requirements for monetization
100hour watchtime | / | 10000 reel view
500 follower

## features
Phase | Tasks |  | Duration (days)
Pre Development | Assets | ✔️ | 3
| UI/UX design | ✔️ | 7
Web Development | django setup | ✔️ | 3
| Video upload, play, reels, like-comment-share, | ✔️ | 10
| Feed | ✔️ | 5
| Reels feed | ✔️ | 4
| Database setup | ✔️ | 3
| Tag management |  | 4
| User login, registration, authentication, | ✔️ | 7
| Settings, profile | ✔️ | 7
| Publisher account, Dashboard | ✔️ | 7
| Subscription, verification |  | 7
| Content management | ✔️ | 3
| Channel Settings |  | 2
| Sponsored content |  |  | ✔️
| Playlist, favourites, watch later |  | 5 | ❌
| Events | ❌ | 7
| Themes |  | 2
| Advertisements |  | 3
Parental controls
| Email & notifications |  | 3
App Development | App Development |  | 10
| Themes |  | 2
| Notification & security |  | 14
Admin | Payment methods |  | 5
| Admin Panel |  | 14
| Administrative Users |  | 7
| Terms & Conditions, Privacy Policy |  | 7
Post Development | Test |  | 7
| Fixing Bugs |  | 14
| Deployment |  | 14
| Total Duration | 6 months | 186
372